# Project Planning Phase

## Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 26 June 2026 |
| --- | --- |
| Team ID |  |
| Project Name | A Comprehensive Measure of Well-Being |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Dataset Collection & Analysis | USN-1 | Collect HDI dataset and understand features | 3 | High | Team Member 1 |
| Sprint-1 | Data Visualization | USN-2 | Perform EDA using Matplotlib and Seaborn | 3 | High | Team Member 1 |
| Sprint-1 | Data Preprocessing | USN-3 | Handle missing values, clean data, and perform feature selection | 5 | High | Team Member 1 |
| Sprint-2 | Model Development | USN-4 | Train Linear Regression model | 5 | High | Team Member 2 |
| Sprint-2 | Model Evaluation | USN-5 | Evaluate model using R² Score and error metrics | 3 | High | Team Member 2 |
| Sprint-2 | Model Management | USN-6 | Save trained model using Pickle (HDI.pkl) | 2 | Medium | Team Member 2 |
| Sprint-3 | Flask Development | USN-7 | Develop Home Page and HDI Prediction Form | 5 | High | Team Member 3 |
| Sprint-3 | Flask Integration | USN-8 | Integrate Linear Regression model with Flask | 5 | High | Team Member 3 |
| Sprint-3 | Result Management | USN-9 | Display HDI Score and Development Category | 3 | High | Team Member 3 |
| Sprint-4 | Data Visualization | USN-10 | Add Heatmaps, Scatter Plots, and Correlation Matrix | 3 | Medium | Team Member 4 |
| Sprint-4 | Testing & Validation | USN-11 | Test application functionality and validate predictions | 4 | High | Team Member 4 |
| Sprint-4 | Deployment | USN-12 | Deploy application on IBM Cloud / Render / Railway | 4 | Medium | Team Member 4 |
| Sprint-4 | Documentation | USN-13 | Prepare final project report and user documentation | 2 | Medium | Team Member 4 |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | 11 | 2 Days | 25 June 2026 | 26 June 2026 | 11 |
| Sprint-2 | 10 | 2 Days | 27 June 2026 | 28 June 2026 | 10 |
| Sprint-3 | 13 | 2 Days | 29 June 2026 | 30 June 2026 | 13 |
| Sprint-4 | 13 | 2 Days | 1 July 2026 | 2 July 2026 | 13 |